## Sheet1
Project: | Compressed Air System
Date:
Location:
Prepared By:
DAILY PROGRESS REPORT (DPR)
Date | Activity/work | Planned Qty | Actual Qty | Unit | Manpower | Status | Remark | Progress
01-08-2026 | Main Air Pipe Installation | 15 | 8 | m | 4 | In Progress | Installation ongoing | 53.33%
02-08-2026 | Main Air Pipe Installation | 7 | 7 | m | 4 | Complete | Main pipe complete | 100%
03-08-2026 | Branch Air Pipe Installation | 18 | 10 | m | 3 | In Progress | Installation ongoing | 55.56%
04-08-2026 | Isolation Valve Installation | 8 | 5 | Nos | 3 | In Progress | Remaining work | 62.5%